## Sheet1
Semester starts 20 Jan
January	01.20-01.24	Week 1	Literature Analysis
	01.27-01.31	Week 2	Literature Analysis	Data Gathering
February	02.03-02.07	Week 3	Literature Analysis	Data Gathering
	02.10-02.14	Week 4	Literature Analysis		Data Processing
	02.17-02.21	Week 5	Literature Analysis		Data Processing	Preliminary Tests
	02.24-02.28	Week 6					Lit & Met Writing
March	03.03-03.07	Week 7					Lit & Met Writing	Data Analysis
	03.10-03.14	Week 8					Lit & Met Writing	Data Analysis
	03.17-03.21	Week 9					Data Analysis
	03.24-03.28	Week 10					Data Analysis
April	03.31-04.04	Week 11					Data Analysis
	04.07-04.11	Week 12					Results Prep
	04.14-04.18	Week 13					Results Prep
	04.21-04-25	Week 14					Results Prep
May	04.28-05.02	Week 15					Results Writing
	05.05-05.09	Week 16					Discussion Writing
	05.12-05.16	Week 17					Discussion Writing
	05.19-05.23	Week 18					Buffer Time
June	05.26-05.30	Week 19					Buffer Time
	06.02-06.06	Week 20					Presentation Prep
Semester ends 9 Jun

Literature Analysis	30.00%
Data Gathering	5.00%
Data Processing	0.00%
Preliminary Tests	40.00%
Lit/Met Writing	0.00%
Data Analysis	0.00%
Preparation of Results	0.00%
Results Writing	0.00%
Discussion Writing	0.00%
Presentation	0.00%