## Sheet1
Start | End | Week # |  |  |  | Submissions | Regular Meetings Fri 10:30
2025-02-03 | 2025-02-07 | Week 1 | Literature Analysis |  |  |  | Meeting Feb-7
2025-02-10 | 2025-02-14 | Week 2 | Literature Analysis | Data Gathering
2025-02-17 | 2025-02-21 | Week 3 | Literature Analysis | Data Gathering | Additional Testing
2025-02-24 | 2025-02-28 | Week 4 | Literature Analysis | Data Processing |  |  | Meeting Feb-28
2025-03-03 | 2025-03-07 | Week 5 | Literature Analysis | Data Processing
2025-03-10 | 2025-03-14 | Week 6 | Lit & Met Writing | Data Processing |  |  | Meeting Mar-14
2025-03-17 | 2025-03-21 | Week 7 | Lit & Met Writing | Data Analysis
2025-03-24 | 2025-03-28 | Week 8 | Lit & Met Writing | Data Analysis |  |  | Meeting Mar-28
2025-03-31 | 2025-04-04 | Week 9 | Lit & Met Writing | Data Analysis
2025-04-07 | 2025-04-11 | Week 10 | Lit & Met Writing | Data Analysis |  |  | Meeting Apr-11
2025-04-14 | 2025-04-18 | Week 11 | Results Prep | Data Analysis
2025-04-21 | 2025-04-25 | Week 12 | Results Prep | Results Writing |  | FIRST DRAFT by Apr 25 | Meeting Apr-25
2025-04-28 | 2025-05-02 | Week 13 | Results Prep | Results Writing
2025-05-05 | 2025-05-09 | Week 14 | Results Prep | Results Writing |  |  | Meeting May-9
2025-05-12 | 2025-05-16 | Week 15 | Discussion Writing | Results Writing
2025-05-19 | 2025-05-23 | Week 16 | Discussion Writing |  |  |  | Meeting May-23
2025-05-26 | 2025-05-30 | Week 17 | Writing Finalization
2025-06-02 | 2025-06-06 | Week 18 | Buffer Time |  |  | FINAL DRAFT around here | Meeting Jun-6
2025-06-09 | 2025-06-13 | Week 19 | Buffer Time
2025-06-16 | 2025-06-20 | Week 20 | Presentation |  |  | DEFENSE around here | Meeting (?)
Literature Analysis – reading prev. studies and articles, books, taking notes and writing early drafts of literature review.
Data Gathering – acquiring datasets (except SAR data), cleaning up and clipping data, resampling/transforming where needed.
Additional Testing – testing most of the workflow (again), inc. MintPy processing, coherence statistical analysis.
Data Processing – preparing and processing InSAR data on the cloud, cleanup and preparation of InSAR data for analysis
Data Analysis – running MintPy workflows, using datasets and coherence data, doing statistical analysis. Acquiring results.
Results Prep – formatting and preparation of the results, cleanup, styling etc. Creation of tables and maps.
Lit & Met, Results, Discussion Writing – writing the sections of the thesis. Certain sections might be prepared earlier for the first draft.
Writing Finalization – buffer time to correctly format and prepare the thesis document for final draft submission.
Buffer Time/Presentation – additional time to account for mistakes, errors or hold-ups. Preparation for defense.